## Test Report
TEST REPORT
Phase | # Test cases Planned (TC/KLOC) | #Defects Planned (DP/KLOC) | #Test cases Actual (TC/KLOC) | #Defects Actual (DP/KLOC) | % Tests Executed | % Tests Passed | % Tests Fail
Unit Test | 40 | 3 - 4 | 0 | 0 | 100% | 100% | 0%
Integration Test | 30 | 2 - 3 | 420 | 0 | 100% | 100% | 0%
System Test | 20 | 4 - 6 | 748 | 0 | 100% | 100% | 0%
Total | 1800 | 9 - 13 | 1168 | 0 | 100% | 100% | 0%
Phase | Round 1 |  |  |  | Round 2
| Pass | Fail | Untested | Bug | Pass | Fail | Untested | Bug
Unit Test
Integration Test | 120 | 2 | 0 | 0 | 420 | 0 | 0 | 0
System Test | 534 | 87 | 0 | 0 | 650 | 85 | 0 | 0
Total | 654 | 89 | 0 | 0 | 1070 | 85 | 0 | 0
Defects | Logged | %Closed | %Invalid | %Open
Critical | 0 | 0% | 0% | 0%
High | 5 | 0% | 0% | 0%
Medium | 26 | 100% | 0% | 0%
Low | 34 | 100% | 0% | 0%
Total | 65 | 100% | 0% | 0%