## CODE-TC-SRS
| Done | In Progress | Not Start
Use Case No. | Group of functions | Functions | Glossary | PIC (Coding) | Deadline | EndDate | Status | Ghép giao diện | TC | Tested | SRS
GUEST MODULE
UC001 | Register | Register for a normal account | Register for a normal account (reader) | VanTTC | 24/10/2018 | 25/10/2018 | Done | Done | Done |  | Done
UC002 |  | Register for an author account | Register for an author account: User must upload an image of their identity card and wait for approve from admin of website. | VanTTC | 24/10/2019 | 25/10/2019 | Done | Done | Done |  | Done
READER/AUTHOR MODULE
UC003 | Account | Login | Login by registered account | VanTTC | 24/10/2016 | 25/10/2016 | Done | Done | Done | Done | Done
UC004 |  | Logout | Logout | VanTTC | 24/10/2017 | 25/10/2017 | Done | Done | Done | Done | Done
UC005 |  | Edit personal information | Edit personal information includes name, email, address, date of birth. | VanTTC | 2016-08-11 |  | Done | Done | Done | Done | Not Start
UC006 |  | Edit avatar and cover photo | Edit avatar and cover photo | DangVH |  |  | Done | Done | Done | Done | Not Start
UC007 |  | Reset password | Reset password by confirm an auto email. | VanTTC |  |  | Done | Done | Done | Done | Done
UC008 | Post | Create a post | Create a post to introduce about book(s). User has to tag book(s) as the topic of that post. | HuyenPT | 2016-07-11 |  | Done | Done | Done | Done | Done
UC009 |  | Edit a post | Edit caption and book tags of a created post. | HuyenPT |  |  | Done | Done | Done | Done | Done
UC010 |  | Delete a post | Delete posts | HuyenPT |  |  | Done | Done | Done | Done | Done
UC011 |  | Like a post | Like posts | HuyenPT |  |  | Done | Done | Done | Done | Done
UC012 |  | Unlike a post | Unlike posts | HuyenPT |  |  | Done | Done | Done | Done | Done
UC013 |  | Comment on a post | Comment on a post | HuyenPT |  |  | Done | Done | Done | Done | Done
UC014 |  | Delete a comment | Delete comments | HuyenPT |  |  | In Progress | Done | Done | Done | Done
UC015 | Interaction | Follow user account | Follow other account to get their new post on new-feed. | DangVH | 2016-08-11 |  | Done | Done | Done | Done | Not Start
UC016 |  | Send message | Send message to other accounts. | DangVH |  |  | In Progress | In Progress | In Progress | In Progress | Not Start
UC017 |  | Report user account | Report other accounts. | DangVH |  |  | Done | Done | Done | Done | Not Start
UC018 |  | Send join-group request | Send join-group request. After that, users have to wait admin of that group to add them as members. | DangVH | 2016-08-11 |  | Done | Done | Done | In Progress | Not Start
UC019 |  | Leave a group | Members can leave a group themselves. | DangVH | 2016-08-12 |  | Done | Done | Done | Done | Not Start
UC020 |  | Report a group | Report groups. | DangVH |  |  | Done | Done | Done | Done | Not Start
UC021 |  | Get Notification | Users get notification when: + Other users like their post + Other users comment on their post + Other users follow their account | DangVH |  |  | In Progress | Done | In Progress | In Progress | Not Start
UC022 | Group | Create a group | To create a group, users have to tag a book/author as the topic of that group. | DangVH | 2016-02-11 |  | Done | Done | Done | Done | Done
UC023 |  | Edit group information | Edit group profile | DangVH | 2016-02-11 | 2016-07-11 | Done | Done | Done | Done | Done
UC024 |  | Edit group's avatar/cover photo |  | DangVH | 2016-02-11 |  | Done | Done | Done | Done | Done
UC025 |  | Add new members | Add new members by enter account name. | DangVH | 2016-02-11 | 2016-07-11 | Done | Done | Done | Done | Done
UC026 |  | Accept join-group request | Users can send a request to group and admin have right to accept them as members or not. | DangVH | 2016-02-11 |  | Done | Done | Not Start | Done | Done
UC027 |  | Set group's admin | Set other members in group as admins. | DangVH | 2016-02-11 | 2016-07-11 | Done | Done | Not Start | Done | Done
UC028 |  | Remove a member | Admins of a group van remove other members from their group. | DangVH | 2016-02-11 | 2016-07-11 | Done | Done | Not Start | Done | Done
UC029 |  | Create a group post | Create group posts: Members do not need to tag books or authors. | HuyenPT |  |  | In Progress | Done | Done | Done | Done
UC030 |  | Like a group post |  | HuyenPT |  |  | In Progress | Done | Done | Done | Done
UC031 |  | Edit a group post | Edit group posts. | HuyenPT |  |  | In Progress | Done | Done | Done | Done
UC032 |  | Delete a group post | Delete group posts. | HuyenPT |  |  | In Progress | Done | Done | Done | Done
UC033 |  | Comment on a group post |  | HuyenPT |  |  | In Progress | Done | Done | Done | Done
UC034 |  | Delete comment on a group post |  | HuyenPT |  |  | In Progress | Done | Done | Done | Done
UC035 | Book | Rate a book | Rate a book: the highest score is 5 stars. | DangVH | 2016-02-11 | 2016-07-11 | Done | Done | Done | Done | Done
UC036 |  | Comment on a book | Comment about book in its own details page | DangVH |  |  | Done | Done | Done | Done | Not Start
UC037 |  | View a book's details | View details about a book: image, description, rating and comments of readers about that book. | DangVH |  |  | Done | Done | Done | Done | Not Start
UC038 |  | Search book/author/other account/group | Search book/author/other account/group | VanTTC |  |  | In Progress | Done | In Progress | In Progress | Not Start
UC039 |  | View suggested books/authors | BSN system suggests books/authors base on the trend of reading: + Book: by access times + Author: by number of followers | DangVH |  |  | Done | Done | In Progress | In Progress | Not Start
ADMIN MODULE
UC040 | User Accounts Management | Search user | Search user | VanTTC |  |  | Done | Done | In Progress |  | Not Start
UC041 |  | Ban user | If an account is reported, admin of page has right to ban that account of decline the reporting request. | DangVH |  |  | Done | Done | In Progress |  | Not Start
UC042 |  | Unban user | Unban user | DangVH |  |  | Done | Done | In Progress |  | Not Start
UC043 |  | Decline request about reporting an account | If an account is reported, admin of page has right to ban that account of decline the reporting request. | DangVH |  |  | Done | Done | Done | Done | Not Start
UC044 |  | Accept request about creating author account |  | DangVH |  |  | Done | Done | Done | Done | Not Start
UC045 |  | Decline request about creating author account | Accept/decline request about creating author account from guests. | DangVH |  |  | Done | Done | Done | Done | Not Start
UC046 | Groups Management | Band a group | When a group is reported, admin of page can band it. | DangVH |  | 2016-07-11 | Done | Done | Done | done | Not Start
UC047 |  | Unban a group | Unban a group | DangVH |  | 2016-07-11 | Done | Done | Done | done | Not Start
UC048 |  | Decline request about reporting a group |  | DangVH |  | 2016-07-12 | Done | Done | Done | done | Not Start
UC049 | Books Management | Add a new book | Add new books. | DangVH | 28/10/2016 | 29/10/2016 | Done | Done | Done | done | Not Start
UC050 |  | Add a new Category | Add new Categories. | DangVH |  |  | Done | Done | Done | done
UC051 |  | Add an author | Add Authors | VanTTC |  |  | In Progress | In Progress | Done | done | Not Start
UC052 |  | Edit book's information | Edit book's information | DangVH | 28/10/2016 | 29/10/2016 | Done | Done | Done | done | Not Start
UC053 |  | Accept add-book request |  | DangVH | 28/10/2016 | 29/10/2016 | Done | Done | Done | done | Not Start
UC054 |  | Decline add-book request | Approve/decline requests about adding a book | DangVH | 28/10/2017 | 29/10/2017 | Done | Done | Done | Done | Not Start
UC055 | Sliders Management | Add a new slider | Add new sliders to introduce about website. | HuyenPT | 24/10/2016 | 24/10/2016 | Done | Done | Done | Done | Not Start
UC056 |  | Delete a slider | Delete sliders. | HuyenPT | 24/10/2017 | 24/10/2017 | Done | Done | Done | Done | Not Start
UC057 |  | Active/de-active a slider | Active/de-active slides. | HuyenPT |  |  | Done | Done | Done | Done | Not Start
UC058 |  | Show a slider | Display sliders on the login page. | DangVH |  |  | Done |  | Done | Done | Not Start
UC059 | Publishers Management | Add a new publisher | Add new publishers | HuyenPT | 2016-01-11 | 2016-02-11 | Done | done | Done | Done | Not Start
UC060 |  | Edit publisher' information | Edit publishers' information | HuyenPT | 2016-01-11 |  | Done | Done | Done | Done | Not Start
UC061 |  | Delete a publisher | Delete publisher | HuyenPT | 2016-01-11 | 2016-02-11 | Done | Done | Done | Done | Not Start
UC062 | Statistics | View user statistic | View statistic about users: + number of old accounts + number of new accounts | DangVH |  |  | Done | Done | Not Start |  | Not Start
|  | View author statistic | View statistic about authors: + number of old accounts + number of new accounts + authors with largest number of followers
|  | View group statistic | View statistic about groups: + number of old groups + number of new groups
|  | View book statistic | View statistic about books: + number of old books + number of new books + the book in trend: base on number of access time

## DOC
HuyenPT |  | Doc | PIC | Status
DangVH | Report 01 | Project Introduction | HuyenPT | Done
HaiCM |  | Schedule | DangVH VanTTC | Done
YenNTH |  | Project Plan in MS Word | HuyenPT | Done
VanTTC |  | CM Plan | HaiCM | Done
|  | SRS => User | VanTTC | In Progress
|  | Q&A Sheet bang tieng Nhat | YenNTH | In Progress
|  | Progress Report cho giai doan 1 (bang tieng Nhat) | HuyenPT | In Progress
|  | SRS , PP Review check list | YenNTH | Done
| Report 02 | Architecture Design | VanTTC | Done
|  | Screen Design | YenNTH | In Progress
|  | Database Design | VanTTC | Done
|  | Class/Component Design | HuyenPT VanTTC | In Progress
|  | Progress Report cho giai doan 2 (bang tieng Nhat) | HuyenPT | In Progress
|  | Design review checklists |  | In Progress
| Report 03 | Test Plan | YenNTH | Done
|  | Test Cases (System Test case, Integration test cases) | YenNTH | In Progress
|  | Review checklist (cho test cases, Test Plan) | YenNTH | In Progress
|  | Progress Report cho giai doan 3 (Phan Construction co lam Test Case, Plan) | HuyenPT | In Progress
| Report 04 | Source codes | DangVH HuyenPT VanTTC | In Progress
|  | Code review checklist | YenNTH | In Progress
|  | UT Cases | DangVH HuyenPT VanTTC | In Progress
|  | UT Review Check List | YenNTH | In Progress
| Report 05 | Test Report, Test result | HaiCM | In Progress
|  | Quality Report | YenNTH | In Progress
|  | Progress Report (cho giai doan coding in Construction) | HuyenPT | In Progress
| Report 06 | Final documents + source codes |  | In Progress
|  | Installation guide |  | In Progress
|  | User guideline |  | In Progress
|  | Project Result Assessment |  | In Progress
|  | Slides for final presentation | HaiCM | In Progress
| Final | Test Plan | YenNTH | Done
|  | System Test Case | YenNTH HaiCM | In Progress
|  | Unit Test Case | DangVH HuyenPT VanTTC | In Progress
|  | Test Result | HaiCM | In Progress
|  | Test Report | YenNTH | In Progress
|  | Project Introduction | HuyenPT | Done
|  | Project Plan | HuyenPT | Done
|  | CM Plan | HaiCM | Done
|  | Project Schedule | DangVH VanTTC | Done
|  | Risk Management Plan |  | In Progress |  | Done
|  | SRS | HuyenPT | In Progress | Yen | In Progress
|  | Screen Design | YenNTH | In Progress |  | Not Start
|  | Data Design | VanTTC | Done
|  | Class Design | HuyenPT VanTTC | In Progress
|  | Architecture Design | VanTTC | Done
|  | Prototype | YenNTH HaiCM | Done

## TỔNG HỢP
CODING: |  |  | TEST CASE: |  |  | DOC:
| Done | 51 |  | Done | 51 |  | Done | 15
| In Progress | 11 |  | In Progress | 7 |  | In Progress | 30
| Not Start | 0 |  | Not Start | 4 |  | Not Start | 0
| Summary | 62 |  | Summary | 62 |  | Summary | 45
DESIGN |  |  | SRS: |  |  | TEST ROUND 1:
| Done | 59 |  | Done | 26 |  | Done | 51
| In Progress | 2 |  | In Progress | 0 |  | In Progress | 5
| Not Start | 0 |  | Not Start | 35 |  | Not Start | 0
| Summary | 61 |  | Summary | 61 |  | Summary | 56